## Sheet1
Project Name: | Sitara
FasTrack System | Mazie
| Melinda | Project Start | 2020-02-02
|  | Display Week | 2 |  | 2020-02-03 |  |  |  |  | 2020-02-08 |  |  |  |  | 2020-02-13 |  |  |  |  | 2020-02-18 |  |  |  |  | 2020-02-23 |  |  |  |  | 2020-02-28 |  |  |  |  | 2020-03-04 |  |  |  |  | 2020-03-09 |  |  |  |  | 2020-03-14 |  |  |  |  | 2020-03-19 |  |  |  |  | 2020-03-24 |  |  |  |  | 2020-03-29 |  |  |  |  | 2020-04-03 |  |  |  |  | 2020-04-08 |  |  |  |  | 2020-04-13 |  |  |  |  | 2020-04-18 |  |  |  |  | 2020-04-23 |  |  |  |  | 2020-04-28 |  |  |  |  | 2020-05-03 |  |  |  |  | 2020-05-08
 | time axis 2020-02-03 to 2020-05-08
TASK | ASSIGNED TO | PROGRESS | START | END
1. Create an UML diagram through Lucidcharts , Github Repo. |  | 0% | 2020-02-03 | 2020-02-07
2. Create the IEEE Standard required Documentation |  | 0% | 2020-02-10 | 2020-02-14
3. Create the Gantt Charts, Roles and responsibilties, and Finish Required Documents. |  | 0% | 2020-02-17 | 2020-02-21
4. Create clear methods and variables for Client Object. |  | 0% | 2020-02-24 | 2020-02-28
5. Work on All Objects (methods, Variables, classes, Attributes). |  | 0% | 2020-03-02 | 2020-03-06
6. Basic command line program to test functions (simulate fastrak capture). |  | 0% | 2020-03-09 | 2020-03-13
7. Create API functions. |  | 0% | 2020-03-16 | 2020-03-20
8. Setup local database & test API functions (local network)(verify all http methods(get, post, put, delete)) |  | 0% | 2020-03-23 | 2020-03-27
9. Spring Break |  | 0% | 2020-04-01 | 2020-04-03
10. Setup online database, test networking(set up firewall to allow external network access) |  | 0% | 2020-04-06 | 2020-04-10
11. Connect command line program to online database. |  | 0% | 2020-04-13 | 2020-04-17
12. . JUnit testing |  | 0% | 2020-04-20 | 2020-04-24
13. JUnit testing |  | 0% | 2020-04-27 | 2020-04-30
14. Consider some form of GUI(Maybe website) |  | 0% | 2020-05-01 | 2020-05-04
15. Finalize everything for presentation |  | 0% | 2020-05-07