## Sheet1
Tentative Schedule
Melinda | Maize | Sitara
3/1 - 3/7
Work on finalizing Client Methods and start coding functions in Client Class | Work on finalizing Website Methods and start coding functions in Website Class | Work on finalizing Payment Methods and start coding functions in Payment Class
3/8 - 3/14
Finish Client Methods | Finish Website Methods | Finish Payment Methods
3/15 - 3/21
Finish Client Methods | Finish Website Methods | Start trying to connect Payment Method to Client Class
3/22 - 3/28
Command Line testing to test Client Functions | Play with simple website layout | Command Line testing to test Payment Functions
3/29 - 4/4
Work on setting up database | Start working on website functions | Work on setting up database
4/5 - 4/11
Work on setting up database | Work on website | Work on setting up database
4/12- 4/18
Connecting database to website | Connecting database to website | Connecting database to website
4/19- 4/25
Simulate FasTrak | Simulate FasTrak | Simulate FasTrak
4/26- 5/2
Work out bugs | Work out bugs | Work out bugs
5/3 - 5/9
Finalize program and testing | Finalize program and testing | Finalize program and testing