## Sheet1
WEEK OF | TASK(S) | NOTES | TEAM MEMBER
Feb. 3 - 7 | Create clear methods and variables for Client Object |  | TBD
Feb. 10 - 14 | Work on All Objects (methods, Variables, classes, Attributes) |  | TBD
Feb. 17 - 21 | Write most functions & methods |  | TBD
Feb. 24 - 28 | Basic command line program to test functions | simulate fastrak capture | TBD
Mar. 2 - 6 | Create API functions |  | TBD
Mar. 9 - 13 | Setup local database & test API functions (local network) | verify all http methods(get, post, put, delete) | TBD
Mar. 16 - 20 | < extra week to account for difficulties > |  | TBD
Mar. 23 - 27 | Setup online database, test networking | set up firewall to allow external network access | TBD
Mar. 30 - Apr. 3 Spring Break
Apr. 6 - 10 | Connect command line program to online database |  | TBD
Apr. 13 - 17 | Connect command line program to online database |  | TBD
Apr. 20 - 24 | JUnit testing |  | TBD
Apr. 27 - May 1 | Consider some form of GUI | Maybe website | TBD
May 4 - 8 | Finalize everything for presentation |  | TBD
May 11 - 15 Finals Week